## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US1 | Register account | As a student applicant, I want to register an account so that I can use the TA recruitment platform. | Must have | 1 | 1. Student can create an account with university email. 2. Duplicate email is rejected. 3. Account is saved successfully. | 3 | MVP / entry point
US2 | Complete applicant profile | As a student applicant, I want to complete my academic profile so that lecturers can judge my suitability. | Must have | 1 | 1. Student can enter programme, year, skills and previous experience. 2. Required fields are validated. 3. Changes can be saved and edited later. | 3 | Depends on US1
US3 | Upload supporting documents | As a student applicant, I want to upload my CV and transcript so that my qualifications can be reviewed. | Must have | 1 | 1. PDF/DOC files can be uploaded. 2. Invalid file type is rejected. 3. Uploaded files remain linked to the applicant record. | 5 | Document management
US4 | Browse TA vacancies | As a student applicant, I want to browse open TA vacancies so that I can find suitable opportunities. | Must have | 1 | 1. Vacancy list shows module, duties, hours and deadline. 2. Closed vacancies are not shown as open. 3. Applicant can open a vacancy detail page. | 3 | MVP
US5 | Filter and search vacancies | As a student applicant, I want to filter vacancies by module, semester and keyword so that I can find relevant posts faster. | Should have | 1 | 1. Search returns matching vacancies. 2. Filters can be combined. 3. Empty result message is shown clearly. | 3 | Improves usability
US6 | Submit TA application | As a student applicant, I want to submit an application for a vacancy so that I can be considered for the role. | Must have | 1 | 1. Applicant can attach profile and documents to one vacancy. 2. Submission is blocked after deadline. 3. Confirmation message is shown after successful submission. | 5 | Core workflow
US7 | Withdraw application | As a student applicant, I want to withdraw an application before the deadline so that I can correct mistakes or change my decision. | Should have | 2 | 1. Applicant can withdraw only before deadline. 2. Status changes to withdrawn. 3. Lecturer can no longer shortlist a withdrawn application. | 2 | Useful control feature
US8 | Create vacancy posting | As a lecturer, I want to create a TA vacancy so that students can apply for my module. | Must have | 2 | 1. Lecturer can enter module, duties, required skills, hours and deadline. 2. Vacancy is published after saving. 3. Missing mandatory data is flagged. | 5 | Lecturer-side MVP
US9 | Edit or close vacancy | As a lecturer, I want to edit or close a vacancy so that outdated information is not shown to applicants. | Should have | 2 | 1. Lecturer can update vacancy details. 2. Closed vacancy is hidden from new applications. 3. Existing applications remain visible to lecturer. | 3 | Depends on US8
US10 | Set selection criteria | As a lecturer, I want to define selection criteria for a vacancy so that applicants can be evaluated fairly. | Should have | 2 | 1. Lecturer can set desired skills, grade requirements and availability. 2. Criteria are stored per vacancy. 3. Criteria appear in vacancy details. | 3 | Supports fair review
US11 | Review applicant list | As a lecturer, I want to view all applications for a vacancy so that I can compare candidates efficiently. | Must have | 2 | 1. Lecturer can see applicant names, status and key profile data. 2. Lecturer can open attached CV/transcript. 3. Applications are grouped by vacancy. | 5 | Core lecturer workflow
US12 | Shortlist candidates | As a lecturer, I want to shortlist promising applicants so that I can focus on the best candidates. | Must have | 2 | 1. Lecturer can mark an applicant as shortlisted. 2. Shortlisted status is stored. 3. Shortlist can be updated before final decision. | 3 | Selection workflow
US13 | Record hiring decision | As a lecturer, I want to record accept/reject decisions so that recruitment outcomes are clear and traceable. | Must have | 3 | 1. Lecturer can mark an applicant as accepted or rejected. 2. Decision date is stored. 3. Selected applicant is no longer shown as pending. | 3 | Audit trail
US14 | View application outcome | As a student applicant, I want to view the result of my application so that I know whether I have been selected. | Must have | 3 | 1. Applicant can see pending / shortlisted / accepted / rejected status. 2. Status updates are visible after lecturer decision. 3. Applicant sees only their own applications. | 2 | Completes applicant journey
US15 | Verify applicant eligibility | As an administrator, I want to verify whether applicants meet university rules so that only eligible students are appointed. | Must have | 3 | 1. Admin can mark applicant as eligible or ineligible. 2. Ineligible applicants are flagged for lecturers. 3. Verification status is stored for reporting. | 5 | Admin control
US16 | Allocate TA to module | As an administrator, I want to allocate selected applicants to modules so that teaching support can be arranged formally. | Must have | 3 | 1. Admin can assign accepted applicant to a module. 2. Allocation record includes hours or role. 3. Duplicate allocation warning is shown when needed. | 5 | Operational feature
US17 | Send notification emails | As a user, I want to receive notification emails so that I know when important recruitment events happen. | Should have | 4 | 1. Email is sent on application submission. 2. Email is sent when status changes. 3. Email content identifies the related vacancy. | 3 | Communication feature
US18 | Export recruitment report | As an administrator, I want to export recruitment data so that I can review hiring progress and workload. | Could have | 4 | 1. Admin can export vacancy and application summary. 2. Report includes status counts. 3. File can be downloaded in CSV format. | 3 | Reporting
US19 | Role-based access control | As a system administrator, I want different user roles to have different permissions so that data is protected. | Must have | 4 | 1. Applicants cannot edit lecturer functions. 2. Lecturers can access only their vacancies. 3. Admin has full management permission. | 5 | Security / non-functional support
US20 | Conflict and workload warning | As an administrator, I want the system to warn about timetable clashes or excessive TA hours so that assignments stay practical and fair. | Could have | 4 | 1. System flags applicants assigned above workload threshold. 2. System flags timetable conflicts when data exists. 3. Warning is visible before final allocation. | 8 | Advanced feature