## Product Backlog
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US01 | Register account | As a student applicant, I want to register an account so that I can use the TA recruitment system. | Must have | 1 | 1. User can create an account with university email and password. 2. Duplicate email or ID is rejected. 3. Account record is saved successfully. | 3 | Core applicant entry point | 2026-03-23 | 2026-03-29
US02 | Log in | As a student applicant, module organiser (MO), or administrator, I want to log in securely so that I can access the functions relevant to my role. | Must have | 1 | 1. Valid credentials allow access. 2. Invalid credentials show an error message. 3. Users are directed to the correct role dashboard. | 3 | Shared by applicant, MO and administrator | 2026-03-23 | 2026-03-29
US03 | Reset password | As a registered user, I want to reset my password so that I can recover access to my account securely. | Should have | 2 | 1. User can request password reset. 2. New password must meet validation rules. 3. Updated password replaces the old one. | 2 | Merged from password-reset stories | 2026-03-30 | 2026-04-05
US04 | Create applicant profile | As a student applicant, I want to create and edit my profile so that module organisers can evaluate my suitability. | Must have | 1 | 1. Applicant can enter programme, year, skills and experience. 2. Required fields are validated. 3. Profile can be saved and edited later. | 3 | Core applicant information | 2026-03-23 | 2026-03-29
US05 | Upload supporting documents | As a student applicant, I want to upload my CV and supporting documents so that my qualifications can be reviewed. | Must have | 1 | 1. Allowed file types are accepted and invalid types are rejected. 2. Uploaded files remain linked to the applicant profile. 3. User can view or replace uploaded documents. | 5 | Merged CV / resume / transcript stories | 2026-03-23 | 2026-03-29
US06 | Browse TA vacancies | As a student applicant, I want to browse open TA vacancies so that I can find suitable opportunities. | Must have | 1 | 1. Vacancy list shows module, duties, hours and deadline. 2. Closed vacancies are not shown as open. 3. Applicant can open a vacancy detail page from the list. | 3 | Core discovery workflow | 2026-03-23 | 2026-03-29
US07 | View vacancy details | As a student applicant, I want to view full vacancy details so that I can decide whether I should apply. | Must have | 1 | 1. Detail view shows description, requirements, workload and deadline. 2. Data matches the stored vacancy record. 3. Application option is hidden after the deadline. | 2 | Pre-application check | 2026-03-23 | 2026-03-29
US08 | Search and filter vacancies | As a student applicant, I want to search and filter vacancies so that I can find relevant posts faster. | Should have | 2 | 1. User can search by keyword. 2. User can filter by module, semester or category. 3. Empty-result state is shown clearly. | 3 | Merged search / filter / category filter | 2026-03-30 | 2026-04-05
US09 | Submit application | As a student applicant, I want to submit an application for a vacancy so that I can be considered for the role. | Must have | 1 | 1. Applicant can submit one application per vacancy. 2. Submission is blocked after the deadline. 3. Confirmation message is shown and the application is stored. | 5 | Core recruitment workflow | 2026-03-23 | 2026-03-29
US10 | Withdraw application | As a student applicant, I want to withdraw an application before the deadline so that I can correct my choices. | Should have | 2 | 1. Applicant can withdraw only eligible applications. 2. Withdrawn application status is updated. 3. Vacancy application count is refreshed. | 2 | Useful control feature | 2026-03-30 | 2026-04-05
US11 | View application status | As a student applicant, I want to track my application status so that I know the current outcome. | Must have | 2 | 1. Applicant can see pending, shortlisted, accepted or rejected status. 2. Status updates are visible after lecturer decisions. 3. Historical applications remain viewable. | 3 | Completes applicant journey | 2026-03-30 | 2026-04-05
US12 | Save favourite jobs | As a student applicant, I want to save vacancies to a favourites list so that I can apply later. | Could have | 3 | 1. User can mark or unmark a vacancy as favourite. 2. Favourite vacancies appear in a dedicated list. 3. Saved items remain linked to the user account. | 2 | Usability enhancement | 2026-04-06 | 2026-04-09
US13 | Post vacancy | As a module organiser (MO), I want to create a TA vacancy so that students can apply for it. | Must have | 1 | 1. Lecturer can enter module, duties, required skills, hours and deadline. 2. Mandatory fields are validated. 3. New vacancy appears in the vacancy list after saving. | 5 | Core MO workflow | 2026-03-23 | 2026-03-29
US14 | Edit or close vacancy | As a module organiser (MO), I want to edit or close a vacancy so that the posting stays accurate. | Should have | 2 | 1. Lecturer can update vacancy details. 2. Lecturer can close a vacancy manually. 3. Closed vacancies cannot receive new applications. | 3 | Merged edit / close / delete stories | 2026-03-30 | 2026-04-05
US15 | Define selection criteria | As a module organiser (MO), I want to define selection criteria for a vacancy so that candidate review is fair and consistent. | Should have | 2 | 1. Lecturer can set desired skills or academic requirements. 2. Criteria are saved with the vacancy. 3. Review screens display the saved criteria. | 3 | Supports structured selection | 2026-03-30 | 2026-04-05
US16 | Review applicant list | As a module organiser (MO), I want to view all applications for a vacancy so that I can compare candidates efficiently. | Must have | 2 | 1. Lecturer can see applicant names, status and key profile information. 2. Applicant list is linked to the correct vacancy. 3. List updates when new applications arrive. | 5 | Core lecturer review | 2026-03-30 | 2026-04-05
US17 | Review applicant profile and CV | As a module organiser (MO), I want to open an applicant's profile and CV so that I can assess qualifications in detail. | Must have | 2 | 1. Lecturer can view profile details and uploaded documents. 2. Correct files open for the selected applicant. 3. Missing-document cases are shown clearly. | 3 | Merged review CV / download CV stories | 2026-03-30 | 2026-04-05
US18 | Shortlist candidates | As a module organiser (MO), I want to shortlist promising applicants so that I can narrow down the selection. | Should have | 2 | 1. Lecturer can mark or remove shortlist status. 2. Shortlisted candidates are clearly identified. 3. Shortlist is saved per vacancy. | 3 | Intermediate selection step | 2026-03-30 | 2026-04-05
US19 | Record hiring decision | As a module organiser (MO), I want to record accept or reject decisions so that recruitment outcomes are finalised. | Must have | 2 | 1. Lecturer can mark an applicant as accepted or rejected. 2. Decision is saved with timestamp or status history. 3. Applicant status is updated in the applicant view. | 5 | Merged select / reject / accept decision stories | 2026-03-30 | 2026-04-05
US20 | Allocate TA to vacancy | As an administrator, I want to allocate an accepted applicant to a module or activity so that staffing is completed. | Must have | 3 | 1. Admin can assign an accepted applicant to the selected vacancy. 2. Allocation record is saved. 3. Assigned work appears in workload views. | 5 | Operational completion step | 2026-04-06 | 2026-04-09
US21 | View TA workload dashboard | As an administrator, I want to view each TA's total assigned workload so that I can monitor fairness and capacity. | Must have | 3 | 1. System shows all accepted assignments per TA. 2. Total assigned hours are calculated correctly. 3. Admin can identify overloaded or underused TAs from the dashboard. | 5 | Core admin oversight | 2026-04-06 | 2026-04-09
US22 | Conflict and workload warning | As an administrator, I want the system to warn about workload conflicts so that over-allocation can be avoided. | Could have | 4 | 1. System flags TAs above a defined workload threshold. 2. Warning is visible before final allocation. 3. Flag updates after assignment changes. | 8 | Advanced admin feature | 2026-04-10 | 2026-04-12
US23 | Send notifications | As a student applicant, module organiser (MO), or administrator, I want to receive notifications about key recruitment events so that I do not miss important updates. | Should have | 3 | 1. Notifications are generated for application submission and status changes. 2. Message content identifies the related vacancy. 3. Notification record is visible in the system or by email. | 3 | Merged notification / email stories | 2026-04-06 | 2026-04-09
US24 | Export recruitment report | As an administrator, I want to export recruitment data so that I can review results outside the system. | Could have | 4 | 1. Admin can export vacancy and application summary data. 2. Exported file uses an allowed text-based format such as CSV. 3. Export contains accurate totals and statuses. | 3 | Merged reports / CSV export stories | 2026-04-10 | 2026-04-12
US25 | Skill matching recommendation | As a lecturer / MO, I want the system to highlight skills that match the vacancy so that candidate review is faster. | Could have | 4 | 1. System compares vacancy requirements with applicant profile or CV keywords. 2. Matching result is shown consistently for each applicant. 3. Recommendation is presented as support, not automatic final selection. | 5 | Merged AI matching / ranking / CV parsing ideas | 2026-04-10 | 2026-04-12
US26 | Missing skill suggestion | As a student applicant, I want to see missing-skill suggestions so that I can improve future applications. | Could have | 4 | 1. System identifies missing or weak requirement matches. 2. Suggestions are shown clearly to the applicant. 3. Suggestions are explainable and linked to vacancy requirements. | 3 | AI-assisted improvement feedback | 2026-04-10 | 2026-04-12
US27 | Role-based permissions | As an administrator, I want users to have role-based permissions so that sensitive recruitment actions are protected. | Must have | 2 | 1. Applicants cannot access lecturer or admin actions. 2. Lecturers can manage only recruitment functions. 3. Administrators can access oversight and allocation functions. | 5 | Security and access-control story | 2026-03-30 | 2026-04-05
US28 | Use file-based data storage | As the project client, I want the system to store data in text-based files rather than a database so that it follows the coursework constraints. | Must have | 1 | 1. System stores data using txt, CSV, JSON or XML. 2. No database dependency is required. 3. Stored data can be read and updated correctly by the application. | 5 | Mandatory non-functional requirement | 2026-03-23 | 2026-03-29