## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
US1 | User Registration | As a prospective TA, I want to register an account so that I can apply for TA positions. | High | 1 | User can enter personal details and create an account. | 3 | Core feature
US2 | User Login | As a registered user, I want to log in so that I can access the system securely. | High | 1 | User can log in with correct credentials. | 3 | Core feature
US3 | Create Applicant Profile | As a TA applicant, I want to create a detailed profile so that I can showcase my qualifications. | High | 1 | Profile information can be entered and saved. | 5 | Core feature
US4 | Upload Resume/CV | As an applicant, I want to upload my resume so that module organisers can review my background. | High | 1 | System accepts CV upload and stores file. | 2 | Core feature
US5 | Browse Available TA Positions | As an applicant, I want to browse available TA positions so that I can find suitable opportunities. | High | 1 | Job list displayed with key information. | 3 | Core feature
US6 | View Job Details | As an applicant, I want to view detailed job information so that I can understand the requirements. | High | 1 | Job description page displays full info. | 2 | Core feature
US7 | Submit TA Application | As an applicant, I want to apply for a TA position so that I can be considered for the role. | High | 1 | Application submitted and stored. | 5 | Core feature
US8 | Check Application Status | As an applicant, I want to check my application status so that I know the progress. | Medium | 2 | Status visible to applicant. | 3
US9 | Post TA Position | As a module organiser, I want to post TA positions so that students can apply. | High | 2 | Job posting form saves job listing. | 5
US10 | Edit Job Posting | As a module organiser, I want to edit job postings so that I can update requirements. | Medium | 2 | Job details can be updated. | 3
US11 | Delete Job Posting | As a module organiser, I want to delete job postings so that closed positions are removed. | Medium | 2 | Job can be removed from the list. | 2
US12 | View Applications | As a module organiser, I want to view all applications so that I can review candidates. | High | 2 | Application list visible for each job. | 3
US13 | Download Applicant CV | As a module organiser, I want to download applicant CVs so that I can evaluate applicants. | High | 2 | CV file can be opened and downloaded. | 2
US14 | Accept Applicant | As a module organiser, I want to accept an applicant so that they can be hired as TA. | High | 2 | Selection saved and status updated. | 5
US15 | Reject Applicant | As a module organiser, I want to reject an applicant so that unsuitable candidates are filtered. | Medium | 3 | Applicant receives rejection status. | 2
US16 | Admin Dashboard | As an admin, I want to view a dashboard so that I can monitor system activity. | High | 3 | Dashboard displays statistics. | 5
US17 | Manage User Accounts | As an admin, I want to manage user accounts so that I can control access. | Medium | 3 | Admin can enable/disable users. | 3
US18 | View All Job Postings | As an admin, I want to view all job postings so that I can monitor content. | Medium | 3 | Admin can view all jobs. | 3
US19 | Search Jobs by Keyword | As an applicant, I want to search jobs by keyword so that I can find relevant positions faster. | Medium | 3 | Search results appear based on keyword. | 2
US20 | Filter Jobs by Department | As an applicant, I want to filter jobs by department so that I can find positions in my area. | Medium | 3 | Jobs can be filtered by department. | 2
US21 | Email Notifications | As a user, I want to receive email notifications so that I stay informed about important updates. | Medium | 4 | Notification sent when status changes. | 3
US22 | Password Reset | As a user, I want to reset my password so that I can regain access to my account. | Medium | 4 | User can reset password via email. | 3
US23 | Skill Matching Recommendation | As an applicant, I want to receive job recommendations based on my skills so that I find suitable positions. | Low | 4 | System suggests jobs matching skills. | 8 | AI Feature
US24 | Candidate Ranking | As a module organiser, I want to see candidates ranked by suitability so that selection is easier. | Low | 4 | System shows ranking score for candidates. | 8 | AI Feature
US25 | Workload Analysis | As an admin, I want to view TA workload analysis so that I can ensure fair distribution. | Low | 4 | Workload statistics visible to admin. | 5 | AI Feature