## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
US1 | Password reset | As a user, I want to reset my password so that I can recover my account access securely. | High | 1 | 1. User can update password via a security question or email. | 3 | Core security
US2 | Application deadline | As an applicant, I want to see job deadlines so that I can submit my application in time. | High | 1 | 1. Countdown or date shown on each job posting. | 2 | Core feature
US3 | Export to CSV | As an admin, I want to export applicant lists to CSV so that I can process data in Excel. | Medium | 2 | 1. System generates a .csv file with candidate details. | 5 | Data handling
US4 | Message center | As a user, I want a message center to communicate with MOs about job details. | Medium | 2 | 1. Users can send and receive internal text messages. | 5 | Communication
US5 | Interview scheduling | As an MO, I want to schedule interview slots so that I can meet with candidates. | Medium | 2 | 1. MO sets time slots; applicant can select one. | 8 | Workflow
US6 | Save favorite jobs | As an applicant, I want to save jobs to a list so that I can apply for them later. | Low | 3 | 1. A "Save" button adds the job to the user's dashboard. | 2 | UX Improvement
US7 | TA Performance rating | As an MO, I want to rate TAs after a semester so that future MOs can see their history. | Medium | 3 | 1. Rating (1-5 stars) and comments are saved to TA profile. | 3 | Quality control
US8 | Portfolio link | As a TA, I want to add a portfolio URL to my profile to show my previous work. | Low | 2 | 1. Profile includes a clickable field for external links. | 1 | Profile boost
US9 | Job category filter | As an applicant, I want to filter jobs by category (e.g., Grading, Invigilation). | Medium | 2 | 1. Filter dropdown updates the job list results. | 3 | Search
US10 | Email notification | As a user, I want to receive an email for system alerts to stay updated. | Low | 4 | 1. System triggers an external email on status change. | 5 | Integration
US11 | Audit log | As an admin, I want to view a log of system actions to monitor security. | Medium | 3 | 1. Text file records user ID, timestamp, and action. | 5 | Security
US12 | Job templates | As an MO, I want to save job descriptions as templates to repost them easily. | Low | 3 | 1. MO can select "Save as Template" during posting. | 3 | Efficiency
US13 | AI CV Parsing | As a system (AI), I want to extract skills from CV text files to auto-fill profiles. | Low | 4 | 1. AI parses .txt/.json CV and populates skill tags. | 8 | AI Feature
US14 | Auto-flag candidates | As an MO, I want the system to flag applicants who lack mandatory skills. | Medium | 4 | 1. System highlights candidates missing key requirements. | 5 | AI Feature
US15 | Salary estimation | As a TA, I want to see my estimated pay based on working hours. | Medium | 2 | 1. Total hours multiplied by rate is shown in dashboard. | 3 | Finance
US16 | Semester report | As an admin, I want to generate a recruitment report to review hiring stats. | Low | 4 | 1. Summary of total hires and workload is produced. | 8 | Reporting
US17 | Role switching | As a user with dual roles (TA & MO), I want to switch profiles without re-logging. | Medium | 3 | 1. A toggle button allows switching between UI views. | 3 | UX
US18 | AI FAQ Bot | As a new user, I want an AI chatbot to answer questions about the process. | Low | 4 | 1. Bot provides answers based on the project handout. | 8 | AI Feature
US19 | File format check | As a system, I want to verify that uploaded files are in allowed text formats. | High | 1 | 1. Error message if a non-text file (e.g., .exe) is uploaded. | 2 | Constraint
US20 | AI Feedback | As an applicant, I want AI to suggest improvements if my application is rejected. | Low | 4 | 1. AI generates tips based on the job requirements gap. | 8 | AI Feature