## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
US1 | Create applicant profile | As a TA applicant, I want to create a profile so that I can apply for jobs. | High | 1 | Profile information can be entered and saved. | 3 | Core feature
US2 | Login system | As a user, I want to log in so that I can access the system securely. | High | 1 | User can log in with correct credentials. | 3 | Core feature
US3 | Upload CV | As an applicant, I want to upload my CV so that employers can review my experience. | High | 1 | System accepts CV upload and stores file. | 2 | Core feature
US4 | Browse jobs | As an applicant, I want to browse available TA jobs so that I can find suitable positions. | High | 1 | Job list displayed with key information. | 3 | Core feature
US5 | View job details | As an applicant, I want to view job details so that I can understand requirements. | High | 1 | Job description page displays full info. | 2 | Core feature
US6 | Apply for job | As an applicant, I want to apply for a job so that I can be considered. | High | 1 | Application submitted and stored. | 5 | Core feature
US7 | Check application status | As an applicant, I want to check my application status so that I know the progress. | Medium | 2 | Status visible to applicant. | 3
US8 | Post job | As a module organiser, I want to post TA jobs so that students can apply. | High | 2 | Job posting form saves job listing. | 5
US9 | Edit job posting | As a module organiser, I want to edit job postings so that I can correct details. | Medium | 2 | Job details can be updated. | 3
US10 | View applications | As a module organiser, I want to view applications so that I can review candidates. | High | 2 | Application list visible for each job. | 3
US11 | Review CV | As a module organiser, I want to review uploaded CVs so that I can evaluate applicants. | High | 2 | CV file can be opened. | 2
US12 | Select applicant | As a module organiser, I want to select applicants so that jobs can be assigned. | High | 2 | Selection saved and status updated. | 5
US13 | Reject applicant | As a module organiser, I want to reject applicants so that unsuitable candidates are filtered. | Medium | 3 | Applicant receives rejection status. | 2
US14 | Admin view workload | As an admin, I want to check TA workload so that work is balanced. | High | 3 | Workload dashboard visible. | 5
US15 | Admin monitor jobs | As an admin, I want to monitor job postings so that the system remains organised. | Medium | 3 | Admin can view all jobs. | 3
US16 | Manage user accounts | As an admin, I want to manage user accounts so that access is controlled. | Medium | 3 | Admin can enable/disable users. | 3
US17 | Search jobs | As an applicant, I want to search jobs so that I can find relevant opportunities. | Medium | 3 | Search results appear based on keyword. | 2
US18 | Skill matching AI | As a system, I want to match applicant skills with job requirements so that recommendations are better. | Low | 4 | System suggests skill match score. | 8 | AI feature
US19 | Missing skill suggestion | As an applicant, I want to see missing skills so that I know how to improve. | Low | 4 | System displays skill gap. | 5 | AI feature
US20 | Candidate recommendation | As a module organiser, I want recommended candidates so that recruitment is faster. | Low | 4 | System suggests best candidates. | 8 | AI feature
US21 | Workload balancing | As an admin, I want workload balancing suggestions so that TA tasks are distributed fairly. | Low | 4 | System warns if workload exceeds threshold. | 5 | AI feature
US22 | Notification system | As a user, I want notifications so that I know when application status changes. | Medium | 4 | Notification shown when status updates. | 3