## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
|  | This is an example. As a <> I want <> So that <> |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3 | Estimation (Story Points)
US1 | Create applicant profile | As a TA applicant, I want to create a personal profile with basic information (name, student ID, contact details, skills, academic background) so that I can complete job applications for TA positions. | High | 1 | 1. Applicant can enter all required profile fields 2. System validates mandatory fields (no empty submission) 3. Profile data is saved to a text/CSV/JSON file 4. Applicant can view their saved profile at any time | 3 | Core feature - Foundation for all applicant actions
US2 | Login system | As a system user (TA applicant, MO, Admin), I want to log in with a unique username and password so that I can access role-specific system features securely. | High | 1 | 1. Separate login interfaces for different user roles 2. System validates credentials against stored user data 3. Incorrect credentials trigger an error message 4. Logged-in users are directed to role-specific homepages 5. User session is maintained for the active period | 3 | Core feature - Access control for all system functions
US3 | Upload CV | As a TA applicant, I want to upload my CV file (PDF/Word/TXT) so that Module Organisers can review my professional and academic experience. | High | 1 | 1. System supports upload of common text-based file formats 2. File size limit is clearly indicated (and enforced) 3. Uploaded CV is linked to the applicant’s profile 4. CV file is stored in the system directory with a unique identifier 5. Applicant can view/delete their uploaded CV | 2 | Core feature - Key application document for MO review
US4 | Browse jobs | As a TA applicant, I want to browse a list of available TA jobs (module support, invigilation) so that I can identify suitable positions to apply for. | High | 1 | 1. Job list displays key info: job title, type (module/invigilation), MO name, deadline, basic requirements 2. List is sorted by application deadline (newest first) by default 3. Job list updates in real-time as new jobs are posted 4. Applicant can refresh the job list manually | 3 | Core feature - Primary job discovery for applicants
US5 | View job details | As a TA applicant, I want to view full details of a specific TA job so that I can confirm if I meet the requirements before applying. | High | 1 | 1. Job detail page shows all info: full description, required skills, workload, deadline, MO contact 2. Page is accessible by clicking on a job in the browse list 3. All job details are pulled from the stored job posting data 4. Job details are static once posted (until MO edits) | 2 | Core feature - Pre-application due diligence for applicants
US6 | Apply for job | As a TA applicant, I want to submit an application for a selected TA job so that I can be considered for the position by the Module Organiser. | High | 1 | 1. Application button is visible only on eligible job detail pages (before deadline, no duplicate application) 2. Application submits with a single click (no additional form for core application) 3. System confirms successful application with a message 4. Application data (applicant ID, job ID, application date) is stored 5. Duplicate applications for the same job are blocked | 5 | Core feature - Core applicant action for recruitment
US7 | Check application status | As a TA applicant, I want to view the status of all my job applications (Pending, Selected, Rejected) so that I can track the recruitment progress. | Medium | 2 | 1. Applicant has a dedicated "My Applications" page 2. Each application shows job title, application date, and current status 3. Status updates in real-time as MO/Admin makes decisions 4. Applicant can filter applications by status (Pending/Selected/Rejected) | 3 | Supports applicant transparency - Reduces MO query volume
US8 | Post job | As a Module Organiser (MO), I want to post a TA job listing (module support/invigilation) with all relevant details so that TA applicants can view and apply for the position. | High | 2 | 1. MO has a dedicated "Post Job" form with all required fields (title, type, description, skills, workload, deadline) 2. System validates mandatory fields (no empty job posting) 3. Posted job is added to the public job browse list 4. Job posting data is saved to a text/CSV/JSON file 5. MO can view all their posted jobs in a dedicated list | 5 | Core feature - Primary MO action for recruitment
US9 | Edit job posting | As a Module Organiser (MO), I want to edit the details of a job I have posted so that I can correct errors or update requirements before the application deadline. | Medium | 2 | 1. MO can only edit jobs they have posted and that are still open (before deadline) 2. All job fields are editable (matching the post job form) 3. Edits are saved and reflected in the public job detail page immediately 4. System logs the edit date for audit purposes 5. Closed jobs (after deadline) are not editable | 3 | Improves job posting accuracy - Reduces admin overhead
US10 | View applications | As a Module Organiser (MO), I want to view a list of all applications for each job I have posted so that I can review and evaluate candidates. | High | 2 | 1. MO has a "My Jobs" page with a link to applications for each posted job 2. Application list shows applicant name, profile link, CV link, application date 3. List is sorted by application date (newest first) by default 4. MO can filter applications by status (Pending/Selected/Rejected) | 3 | Core feature - MO candidate review foundation
US11 | Review CV | As a Module Organiser (MO), I want to open and view the CV uploaded by a TA applicant so that I can evaluate their experience and skills for the job. | High | 2 | 1. CV link is visible next to each applicant in the application list 2. Clicking the link opens the CV file in the system (or default OS viewer) 3. MO can only view CVs for applicants to their posted jobs 4. CV file access is restricted to authorised MOs only | 2 | Core feature - Key MO candidate evaluation step
US12 | Select applicant | As a Module Organiser (MO), I want to select a TA applicant for a job so that the applicant is marked as successful and their status is updated. | High | 2 | 1. MO has a "Select" button next to each pending applicant in the application list 2. Selecting an applicant triggers a confirmation message 3. Applicant’s application status is updated to "Selected" (reflected in applicant’s view) 4. Selection data (MO ID, applicant ID, job ID, selection date) is stored 5. MO can view a list of all selected applicants for their jobs | 5 | Core feature - Core MO recruitment decision action
US13 | Reject applicant | As a Module Organiser (MO), I want to reject a TA applicant for a job so that the applicant is marked as unsuccessful and their status is updated. | Medium | 3 | 1. MO has a "Reject" button next to each pending applicant in the application list 2. Rejecting an applicant triggers a confirmation message 3. Applicant’s application status is updated to "Rejected" (reflected in applicant’s view) 4. Rejection data (MO ID, applicant ID, job ID, rejection date) is stored 5. MO can add an optional short reason for rejection (stored with data) | 2 | Streamlines candidate filtering - Reduces applicant uncertainty
US14 | Admin view workload | As an Admin, I want to view a dashboard of the overall TA workload (assigned jobs per TA) so that I can ensure fair distribution of TA tasks across the school | High | 3 | 1. Admin has a dedicated "TA Workload" dashboard 2. Dashboard displays TA name, student ID, number of assigned jobs, total workload hours 3. Workload data is pulled from selected applicant/job data 4. Dashboard can be sorted by total workload hours (highest/lowest) 5. Dashboard updates in real-time as new selections are made | 5 | Core Admin feature - Workload balance (project AI precursor)
US15 | Admin monitor jobs | As an Admin, I want to view a complete list of all job postings (open/closed, all MOs) so that I can monitor the school’s TA recruitment activity and keep the system organised. | Medium | 3 | 1. Admin has a dedicated "All Jobs" monitor page 2. Job list shows all details (MO name, job type, status, deadline, number of applications) 3. Admin can filter jobs by status (Open/Closed), MO, or job type 4. Admin can mark inactive jobs as "Closed" manually 5. System shows a summary of total open/closed jobs at the top | 3 | Admin oversight - Ensures system hygiene and recruitment visibility
US16 | Manage user accounts | As an Admin, I want to manage system user accounts (create, enable, disable) for TA applicants, MOs, and other Admins so that I can control system access and remove inactive users. | Medium | 3 | 1. Admin has a dedicated "User Management" page with a full user list 2. List shows user ID, name, role, account status (Active/Inactive), creation date 3. Admin can disable/inactive any user account (prevents login) 4. Admin can re-enable inactive user accounts 5. Admin can create new MO/Admin accounts (TA accounts self-created) | 3 | Access control - Critical for system security and management
US17 | Search jobs | As a TA applicant, I want to search for TA jobs using keywords (job title, skill, module name) so that I can quickly find relevant job opportunities without browsing the full list. | Medium | 3 | 1. Search bar is visible at the top of the job browse page 2. System returns matching jobs based on keyword in any job field 3. Search results are displayed in the same format as the browse list 4. Empty search returns the full job list 5. Search is case-insensitive for ease of use | 2 | Quality of life feature - Improves applicant job discovery efficiency
US18 | Skill matching AI | As the system, I want to automatically match TA applicant skills (from profile) with job required skills (from posting) and generate a match score (0-100%) so that MOs and applicants get data-driven skill alignment recommendations. | Low | 4 | 1. System extracts skills from applicant profile and job posting (structured text) 2. Generates a numerical match score (0-100%) based on skill overlap 3. Match score is displayed next to applicant name in MO’s application list 4. Match score is displayed next to job title in applicant’s job list 5. Score calculation logic is transparent (documented in user manual) | 8 | AI feature - Project advanced requirement, skill alignment
US19 | Missing skill suggestion | As a TA applicant, I want the system to identify and display the skills I am missing for a specific job (based on skill matching) so that I know how to improve my profile for future TA applications. | Low | 4 | 1. Missing skills are displayed on the job detail page (for logged-in applicants) 2. Suggestions are based on the skill matching AI score (skills in job not in profile) 3. Missing skills are listed in order of job priority (core vs nice-to-have) 4. Applicant can click a skill to add it to their profile (if relevant) | 5 | AI feature - Builds on US18, applicant development support
US20 | Candidate recommendation | As a Module Organiser (MO), I want the system to recommend the top TA applicants for a job (based on skill match score and profile completeness) so that I can speed up the candidate review process. | Low | 4 | 1. System generates a "Top Candidates" section on the MO’s application list 2. Recommendations are sorted by skill match score (highest first) then profile completeness 3. MO can toggle the recommendation section on/off 4. Recommendation logic is transparent (documented in user manual) 5. Recommendations update in real-time as new applications are received | 8 | AI feature - Builds on US18, MO recruitment efficiency
US21 | Workload balancing | As an Admin, I want the system to provide workload balancing suggestions (AI-driven) and warn if a TA’s assigned workload exceeds a set threshold so that TA tasks are distributed fairly across the school. | Low | 4 | 1. Admin sets a configurable workload threshold (hours/jobs) in the system 2. System flags TAs with workload exceeding the threshold (red highlight on dashboard) 3. System suggests reallocating jobs from overloaded TAs to underloaded TAs 4. Suggestions are based on skill match between unassigned jobs and underloaded TAs 5. Workload balance warnings are visible on the Admin dashboard at all times | 5 | AI feature - Builds on US14, advanced workload management
US22 | Notification system | As a system user (TA applicant, MO, Admin), I want to receive real-time in-system notifications for key events (application status change, new application, workload alert) so that I am informed of important system activity without checking manually. | Medium | 4 | 1. Notifications icon is visible on the top navigation bar for all logged-in users 2. Unread notifications show a numerical badge (count) 3. Key events trigger notifications: application status change (TA), new application (MO), workload threshold breach (Admin) 4. Notifications show event detail, date/time, and a link to the relevant page 5. User can mark notifications as read/delete them | 3 | Quality of life feature - Improves system usability and user engagement