## Sheet
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US01 | Register Account | As a TA, I want to create an account so that I can apply for jobs | High | 1 | User can register with email, password validation, and data stored in file | 5 | Core
US02 | Login | As a TA, I want to login so that I can access system | High | 1 | Correct credentials login; wrong shows error | 3 | Core
US03 | Create Profile | As a TA, I want to create profile so that MO can evaluate me | High | 1 | Profile includes skills, experience, saved in file | 5
US04 | Upload CV | As a TA, I want to upload CV so that my qualifications are visible | High | 1 | CV uploaded as file path and retrievable | 3
US05 | Browse Jobs | As a TA, I want to browse jobs so that I can find opportunities | High | 1 | List jobs from file; filter by module | 5
US06 | Apply Job | As a TA, I want to apply so that I can get selected | High | 1 | Application stored and linked to job+user | 8 | Core
US07 | View Application Status | As a TA, I want to check status so that I know results | Medium | 2 | Status updates visible: pending/accepted/rejected | 3
US08 | MO Post Job | As MO, I want to post jobs so that I can recruit TAs | High | 1 | Job info stored and displayed | 5 | Core
US09 | MO Edit Job | As MO, I want to edit jobs so that I can update requirements | Medium | 2 | Job editable and saved | 3
US10 | MO Select Applicants | As MO, I want to select applicants so that I assign TAs | High | 2 | Can mark accepted/rejected | 5 | Core
US11 | Admin View Workload | As admin, I want to check workload so that I balance tasks | Medium | 3 | System aggregates assigned jobs per TA | 8
US12 | Search Jobs | As TA, I want search so that I find jobs faster | Medium | 2 | Keyword search works | 3
US13 | Filter Jobs | As TA, I want filters so that I narrow results | Low | 3 | Filter by module/time | 2
US14 | Notification | As user, I want notifications so that I know updates | Low | 4 | Notify on application result | 3
US15 | Logout | As user, I want logout so that session ends securely | High | 1 | Session cleared | 1
US16 | Skill Matching (AI) | As system, I want match skills so that recommend jobs | Medium | 3 | Basic keyword matching implemented | 8 | AI feature
US17 | Missing Skills Suggestion | As TA, I want suggestions so that I improve profile | Low | 4 | System shows missing keywords | 5 | AI feature
US18 | Workload Balancing | As admin, I want balance workload so that fairness ensured | Medium | 4 | Limit max assignments per TA | 8 | AI/logic
US19 | Error Handling | As system, I want error handling so that system stable | High | 2 | Invalid input handled gracefully | 3
US20 | Data Storage (File) | As system, I want store data in files so that requirement met | High | 1 | All data saved in txt/json | 5 | Mandatory
US21 | User Validation | As system, I want validate input so that data correct | High | 2 | Email/password rules enforced | 3
US22 | View Assigned Jobs | As TA, I want see assigned jobs so that I track work | Medium | 3 | Accepted jobs listed | 3
US23 | Admin Reports | As admin, I want reports so that I see stats | Low | 4 | Summary counts generated | 5
US24 | Prototype UI | As team, we want UI so that system usable | High | 1 | Basic UI screens exist | 5 | Assessment
US25 | Testing Cases | As team, we want tests so that system verified | Medium | 3 | Basic test cases documented | 5
US26 | GitHub Integration | As team, we want version control so that contributions tracked | High | 1 | Repo with commits exists | 3 | Requirement